## Cover Sheet
CHANNING SCHOOL
ACCESSIBILITY PLAN JUNIOR SCHOOL
This policy also applies to the EYFS
Updated | Review Date | Version
2024-04-01 | 2025-04-01 | 24.1
Reviewed by: Caron Hesketh (H&S and Transport Manager)
Approved by: Roy Hill (Bursar)
Signed by: Board of Governors (Estates Committee)
Accessibility Plan 2024-2026
To be read in conjunction with the Accessibility Audit and Plan 27.10.2023 undertaken by Equality Act Audits
Name of Auditor: Leslie Mifsud, Lead Auditor
Channing Junior School
High Street
Highgate
North London

## Action Plan
Audit ref | Audit Item | Suggested Action | Target date for completion | Ownership of Task | Proposed works date | Date Completed
10.2.2 | Arrangements for disabled parking | 1) Mark out an accessible car park bay | 2024 | M Blase | Summer 2024
|  | 2) Place a sign at the entrance showing that there is accessible parking and where it is | 2024 | M Blase | Summer 2024
|  | 3) Erect a sign in front of the bay at a height of 1 metre | 2024 | M Blase | Summer 2024
|  | 4) Mark out a safe walkway in the carpark | 2024 | M Blase | Summer 2024
|  | 5) Add a note to our website stating that there is a disabled bay if required | 2024 | M Blase | Easter half term | 13/02/2024 - website updated to state that should they require parking then they can contact us to dicsuss arrangments
10.2.5 | Reception Facilities | 1) Install a portable hearing loop and clearly display the sign | 2024 | M Blase | Octboer 2024
|  | 2) Provide either signage or instructions from the reception area to the visitors accessible toilet | 2024 | M Blase | Octboer 2024
|  | 3) Provide a seat with a high back and arms | 2024 | M Blase | Easter half term | Completed 4th March 2024
10.2.6 | External areas, movement between buildings | 1) Install further handrails to outside steps where there are more than 3 risings and where needed. All steps with 3 or more risings should have handrails fitted on both sides | 2025 | M Blase | Review in October 2024 and if required install in Summer 2025
|  | 2) Ensure that all outside steps have nosings. nosings should be 2 inch strips which are painted or attached to the front and top of each step. Usually, yellow is used as it's a good contrasting colour. | Ongoing | M Blase | Start in Summer 2024
|  |  | 2024 | M Blase
10.2.10 | Accessible toilets | 1) All accessible toilets to have mirrors, shelves and coat hooks fitted as an accessible height | 2024 | M Blase | Review/start works in Summer 2024 where applicable
|  | 2) All accessible toilets to be clear of clutter | 2024 | M Blase | Review/start works in Summer 2024 where applicable
|  | 3) Emergency alarm cords to be loose (able to be reached from the ground) | 2024 | M Blase | Review/start works in Summer 2024 where applicable
|  | 4) All accessible toilets to have flashing lights installed to notify a deaf person of the fire alarm activation | 2024 | M Blase | Review/start works in Summer 2024 where applicable
|  | 5) Training to be arranged so that staff know how to respond to an activation of the emergency beacon | 2024 | M Blase | Review/start works in Summer 2024 where applicable
10.2.13 | Internal signage | Review signage and ensure it is all in both uppercase and lowercase lettering | Ongoing | N/A | N/A | Not being taken forward
10.2.18 | Doors | Change non-compliant door handles to the D style if handle (example in report) | 2026 | M Blase | To be reviewd in 2025
10.2.20 | Staff Facilities | Provide at least 1 high backed chair in the staff room | 2024 | M Blase | Easter half term | Completed 4th March 2024
10.3.1 | Training & Accreditation of Teachers and teaching Assistants | Provide training in disability awareness to staff, governors and pupils | N/A | R HIll/C hesketh | September 2024 Inset day

## Table of Audit Findings
Table of Audit Findings
This table summarises the audit outcomes. The detailed findings are given in Section 10 below.
Action Plan recommendations, where appropriate, are provided in Section 13.
Reference | Audit Aspect | Outcome 2023
Access to Information
10.1.1 | Staff Training – Is awareness training provided to enable all staff to understand and recognise disability issues? | Compliant
10.1.2 | Arrangements for providing information in simple language, large print, via digital audio, by Braille | Compliant
10.1.3 | Is the school website and social media content accessible? | Compliant
10.1.4 | Is information presented to groups in a user-friendly way for people with disabilities which affect their vision? | Compliant
10.1.5 | Staff familiarity with technologies and support strategies and processes developed to assist people with disabilities | Compliant
10.1.6 | Complaints process | Compliant
Access to Site and Facilities
10.2.1 | Access via Public Transport | Compliant
10.2.2 | Arrangements for disabled parking | Improvement Recommended
10.2.3 | Security gates and barriers | Exemplary
10.2.4 | Access through the site to Reception | Compliant
10.2.5 | Reception facilities | Improvement Recommended
10.2.6 | External areas, movement between buildings | Improvement Recommended
10.2.7 | Emergency Evacuation and Lockdown Procedures | Compliant
10.2.8 | Internal movement – corridors and evacuation routes | Compliant
10.2.9 | Internal movement – stairs and lifts | Compliant
10.2.10 | Accessible Toilets | Improvement Recommended
10.2.11 | Changing Rooms | Exemplary
10.2.12 | Medical Facilities | Exemplary
10.2.13 | Internal Signage | Improvement Recommended
10.2.14 | Internal décor and finishes | Compliant
10.2.15 | Lighting | Compliant
10.2.16 | Dining and Catering | Exemplary
10.2.17 | Social spaces & quiet spaces | Compliant
10.2.18 | Doors | Improvement Recommended
10.2.19 | Teaching and study spaces, Furniture & teaching Equipment | Compliant
10.2.20 | Staff facilities | Improvement Recommended
Access to Education
10.3.1 | Training & accreditation of Teachers and Teaching Assistants | Improvement Recommended
10.3.2 | Pre-admission visits | Compliant
10.3.3 | Admission | Compliant
10.3.4 | Safeguarding | Exemplary
10.3.5 | Pupils with Temporary, Emerging or ongoing Health Care Needs | Compliant
10.3.6 | Access to the Curriculum | Exemplary
10.3.7 | Lesson planning and support for pupils with disabilities and SEN | Exemplary
10.3.8 | Access to Educational Visits and Extra Curricular Activities | Exemplary
10.3.9 | Pupil Outcomes | Compliant
10.3.10 | Staffing & Leadership | Compliant